## Sheet1
| Energy-Based Learning for Weakly-Supervised Visual Relationship Detection |  |  | Berkay GÜLER
|  | Milestones | Estimated Work Hours(p/week) | Accumulated Total Hour
1st Term | 10--16 Oct | Start learning Pytorch 1. Image Classification(MNIST) 2. Object Detection(Pascal VOC) | 12--18 | 12--18
| 17--23 Oct |  | 20--30 | 32--48
| 24--30 Oct | Finish most literature work 1. Faster R-CNN[1], Strongly SGG Papers[2,3,4,5,6,7] 2. Weakly Supervised SGG Papers[8] | 12--18 | 44--66
| 31--6 Nov |  | 32--36 | 76--102
| 7--13 Nov | 1. Meeting w/promoter(3-4 slides), 2. Read EBM papers [9] | 20--26 | 96--128
| 14--20 Nov | 1. Run Example Paper[6] Code(Testing) 2. Study Visual genome dataset | 20--26 | 116--154
| 21--27 Nov | Run Example Paper Code(Training-Strongly Supervised) 1. Understand code and model 2. Modify and see its effects | 16--24 | 132--178
| 28--4 Dec |  | 24--32 | 156--210
| 5--11 Dec | Example Paper Model discussion 1. Results Visualization(Why EBM works?) Start brainstorming for Weakly SGG ideas | 12--18 | 168--228
| 12--18 Dec | Brainstorming for weakly training(How to implement?) | 32--40 | 200--268
| 19--25 Dec | Mid-presentation | 8 | 208--276
| 26--1 Jan | NO WORK
2--8 Jan
Exams | 9--15 Jan
16--22 Jan
23--29 Jan
30-5 Feb
2nd Term | 6-12 Feb | Brainstorming for weakly training(How to implement?) 1. Read new papers[...] about weakly training | 40 | 248--316
| 13--19 Feb |  | 36--42 | 284--358
| 20--26 Feb | Apply new idea 1. Analyze and test it. | 32--38 | 316--396
| 27--5 Mar |  | 36--42 | 352--438
| 6--12 Mar | Find new idea if previous one is not working 1. Analyze and test it. | 28--34 | 380--472
| 13--19 Mar |  | 32--38 | 412--510
| 20--26 Mar | Find new idea if previous one is not working 1. Analyze and test it. Major block of work should be done at this point. (Intermediary Results) | 32--38 | 444--548
| 27--2 Apr |  | 32--38 | 476--586
Spring Break | 3--9 Apr |  | 40--48 | 516--634
| 10--16 Apr |  | 40--48 | 556--682
2nd Term | 17--23 Apr |  | 32--38 | 588--720
| 24--30 Apr | Final model / Test results | 28--34 | 616--754
| 1-30 May | Write thesis report / More Testing
References
[1] Ren, S., He, K., Girshick, R., & Sun, J. (2015). Faster r-cnn: Towards real-time object detection with region proposal networks. Advances in neural information processing systems, 28. [2]Tang, K., Niu, Y., Huang, J., Shi, J., & Zhang, H. (2020). Unbiased scene graph generation from biased training. In Proceedings of the IEEE/CVF conference on computer vision and pattern recognition (pp. 3716-3725). [3]Tang, K., Zhang, H., Wu, B., Luo, W., & Liu, W. (2019). Learning to compose dynamic tree structures for visual contexts. In Proceedings of the IEEE/CVF conference on computer vision and pattern recognition (pp. 6619-6628). [4]Xu, D., Zhu, Y., Choy, C. B., & Fei-Fei, L. (2017). Scene graph generation by iterative message passing. In Proceedings of the IEEE conference on computer vision and pattern recognition (pp. 5410-5419).
[5] Zellers, R., Yatskar, M., Thomson, S., & Choi, Y. (2018). Neural motifs: Scene graph parsing with global context. In Proceedings of the IEEE conference on computer vision and pattern recognition (pp. 5831-5840). [6] Suhail, M., Mittal, A., Siddiquie, B., Broaddus, C., Eledath, J., Medioni, G., & Sigal, L. (2021). Energy-based learning for scene graph generation. In Proceedings of the IEEE/CVF conference on computer vision and pattern recognition (pp. 13936-13945). [7]Kumaraswamy, S. K., Shi, M., & Kijak, E. (2021). Detecting human-object interaction with mixed supervision. In Proceedings of the IEEE/CVF Winter Conference on Applications of Computer Vision (pp. 1228-1237). [8] Peyre, J., Sivic, J., Laptev, I., & Schmid, C. (2017). Weakly-supervised learning of visual relations. In Proceedings of the ieee international conference on computer vision (pp. 5179-5188).
[9]LeCun, Y., Chopra, S., Hadsell, R., Ranzato, M., & Huang, F. (2006). A tutorial on energy-based learning. Predicting structured data, 1(0).